## Graf. % Praticas Específicas
| REQM | PP | PMC | SAM | MA | PPQA | CM
ND | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
PD | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
LD | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
TD | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!

## PMC
PMC - Project Monitoring and Control |  | Processo da Organização
Cód. | Práticas Específicas | Atividade | Evidências objetivas (artefatos) | Status Def.
PMC SP 1.1 | SP 1.1 Monitor Project Planning Parameters Monitor the actual values of the project planning parameters against the project plan. Project planning parameters constitute typical indicators of project progress and performance and include attributes of work products and tasks, cost, effort, and schedule. Attributes of the work products and tasks include such items as size, complexity, weight, form, fit, or function. Monitoring typically involves measuring the actual values of project planning parameters, comparing actual values to the estimates in the plan, and identifying significant deviations. Recording actual values of the project planning parameters includes recording associated contextual information to help understand the measures. An analysis of the impact that significant deviations have on determining what corrective actions to take is handled in the second specific goal and its specific practices in this process area. Typical Work Products 1. Records of project performance 2. Records of significant deviations Subpractices 1. Monitor progress against the schedule. Progress monitoring typically includes the following: · Periodically measuring the actual completion of activities and milestones · Comparing actual completion of activities and milestones against the schedule documented in the project plan · Identifying significant deviations from the schedule estimates in the project plan 2. Monitor the project's cost and expended effort. Effort and cost monitoring typically includes the following: · Periodically measuring the actual effort and cost expended and staff assigned · Comparing actual effort, costs, staffing, and training to the estimates and budgets documented in the project plan · Identifying significant deviations from the budgets in the project plan 3. Monitor the attributes of the work products and tasks. Refer to the Project Planning process area for information about the attributes of work products and tasks. Monitoring the attributes of the work products and tasks typically includes the following: · Periodically measuring the actual attributes of the work products and tasks, such as size or complexity (and the changes to the attributes) · Comparing the actual attributes of the work products and tasks (and the changes to the attributes) to the estimates documented in the project plan · Identifying significant deviations from the estimates in the project plan 4. Monitor resources provided and used. Refer to the Project Planning process area for information about planned resources. For Software Engineering Examples of software-engineering resources include the following: · Host computers and peripherals · Networks · Software test computers and peripherals · Target computer environment software · Software-engineering environment (e.g., software tools) Examples of resources include: · Physical facilities · Computers, peripherals, and software used in design, manufacturing, testing and operation · Networks · Security environment · Project staff · Processes 5. Monitor the knowledge and skills of project personnel. Refer to the Project Planning process area for information about planning for knowledge and skills needed to perform the project. Monitoring the knowledge and skills of the project personnel typically includes the following: · Periodically measuring the acquisition of knowledge and skills by project personnel · Comparing the actual training obtained to that documented in the project plan · Identifying significant deviations from the estimates in the project plan 6. Document the significant deviations in the project planning parameters. | 1. Atualizar o Iteration Burndown chart diariamente. 2. Atualizar o Release Burndown chart a cada final de iteração. 3. Atualizar o gráfico de valor agregado toda semana. 4. A cada atualização de gráficos, gerar um registro de desvios significativos notados no gráfico. | 1. Iteration Burndown chart (dias da sprint versus quantidade de horas restantes). 2. Release Burndown chart (iterações do projeto versus pontos restantes para o projeto). 3. Gráfico do valor agregado (iterações do projeto versus valores em reais, duas curvas: custo real e custo estimado). 4. Notas anexadas a cada gráfico com observações sobre os desvios significativos notados.
PMC SP 1.2 | SP 1.2 Monitor Commitments Monitor commitments against those identified in the project plan. Typical Work Products 1. Records of commitment reviews Subpractices 1. Regularly review commitments (both external and internal). 2. Identify commitments that have not been satisfied or which are at significant risk of not being satisfied. 3. Document the results of the commitment reviews. | 1. Realizar uma reunião rápida diária, onde cada membro do time diz o que fez no dia, o que vai fazer após a reunião e se há algum impedimento para a realização desta atividade. | 1. Registro da reunião (ata e depoimentos gravados).
PMC SP 1.3 | SP 1.3 Monitor Project Risks Monitor risks against those identified in the project plan. Refer to the Project Planning process area for more information about identifying project risks. Refer to the Risk Management process area for more information about risk management activities. Typical Work Products 1. Records of project risk monitoring Subpractices 1. Periodically review the documentation of the risks in the context of the project's current status and circumstances. 2. Revise the documentation of the risks, as additional information becomes available, to incorporate changes. 3. Communicate risk status to relevant stakeholders. Examples of risk status include the following: · A change in the probability that the risk occurs · A change in risk priority | 1. Com o registro dos riscos em mãos, verificar quais continuam ativos, se a prioridade, a probabilidade e o impacto deles mudaram e se os responsáveis por cada risco estão realizando as ações estratégicas escolhidas. Além disso, adicionar novos riscos identificados e analisados. 2. Registrar as mudanças, exclusões e inclusões em documentos de revisão de riscos, criado nos inícios e fins das iterações. | 1. Documentos de revisão de riscos, criado nos inícios e fins das iterações.
PMC SP 1.4 | SP 1.4 Monitor Data Management Monitor the management of project data against the project plan. Refer to the Plan for Data Management specific practice in the Project Planning process area for more information about identifying the types of data that should be managed and how to plan for their management. Once the plans for the management of project data are made, the management of that data must be monitored to ensure that those plans are accomplished. Typical Work Products 1. Records of data management Subpractices 1. Periodically review data management activities against their description in the project plan. 2. Identify and document significant issues and their impacts. 3. Document the results of data management activity reviews. | 1. Revisar o plano de gerenciamento de dados a cada início de iteração, podendo ocorrer modificações no gerenciamento ou inclusão de novos dados necessários ao projeto. 2. Checar se o projeto está seguindo o plano e se todos os dados estão acessíveis aos stakeholders do projeto. | 1. Versões do plano de gerenciamento de dados, com anotações e observações sobre as mudanças realizadas.
PMC SP 1.5 | SP 1.5 Monitor Stakeholder Involvement Monitor stakeholder involvement against the project plan. Refer to the Plan Stakeholder Involvement specific practice in the Project Planning process area for more information on identifying relevant stakeholders and planning the appropriate involvement with them. Once the stakeholders are identified and the extent of their involvement within the project is specified in project planning, that involvement must be monitored to ensure that the appropriate interactions are occurring. Typical Work Products 1. Records of stakeholder involvement Subpractices 1. Periodically review the status of stakeholder involvement. 2. Identify and document significant issues and their impacts. 3. Document the results of the stakeholder involvement status reviews. | 1. Realizar uma reunião ao final de cada iteração para atualizar os stakeholders a respeito do andamento do projeto, do que já foi feito e dos impedimentos existentes. 2. Na mesma reunião, registrar as opiniões e sugestões de mudanças e melhorias dos stakeholders. | 1. Registro da reunião (ata e depoimentos gravados). 2. Ata de Sugestões
PMC SP 1.6 | SP 1.6 Conduct Progress Reviews Periodically review the project's progress, performance, and issues. Progress reviews are reviews on the project to keep stakeholders informed. These project reviews can be informal reviews and may not be specified explicitly in the project plans. Examples of these reviews include the following: · Reviews with staff · Reviews with project engineers and support · Reviews with management Typical Work Products 1. Documented project review results Subpractices 1. Regularly communicate status on assigned activities and work products to relevant stakeholders. Managers, staff members, customers, end users, suppliers, and other relevant stakeholders within the organization are included in the reviews as appropriate. 2. Review the results of collecting and analyzing measures for controlling the project. Refer to the Measurement and Analysis process area for more information about the process for measuring and analyzing project performance data. 3. Identify and document significant issues and deviations from the plan. 4. Document change requests and problems identified in any of the work products and processes. Refer to the Configuration Management process area for more information about how changes are managed. 5. Document the results of the reviews. 6. Track change requests and problem reports to closure. | 1. Confeccionar planilha indicativa do progresso do projeto, apresentando a quantidade de erros, número de casos de uso iniciados, finalizados e em andamento, e o desempenho dos envolvidos nas atividades. 2. Realizar uma reunião a cada 15 dias com os principais gerentes de desenvolvimento e de projeto envolvidos para realizar uma revisão do andamento corrente do projeto para explanação da planilha desenvolvida. 3. Compor planilha comparativa, determinando o andamento do projeto. | 1. Registro da reunião (ata e depoimentos gravados). 2. Planilha Comparativa de Progresso.
PMC SP 1.7 | SP 1.7 Conduct Milestone Reviews Review the accomplishments and results of the project at selected project milestones. Refer to the Project Planning process area for more information about milestone planning. Milestone reviews are planned during project planning and are typically formal reviews. Typical Work Products 1.Documented milestone review results Subpractices 1. Conduct reviews at meaningful points in the project's schedule, such as the completion of selected stages, with relevant stakeholders. Managers, staff members, customers, end users, suppliers, and other relevant stakeholders within the organization are included in the milestone reviews as appropriate. 2. Review the commitments, plan, status, and risks of the project. 3. Identify and document significant issues and their impacts. 4. Document the results of the review, action items, and decisions. 5. Track action items to closure. | 1. Realizar uma reunião de revisão dos prazos no ⅓ final para conclusão do prazo de cada item definido no planejamento de projeto. | 1. Relatório de Revisão de Prazos
PMC SP 2.1 | SP 2.1 Analyze Issues Collect and analyze the issues and determine the corrective actions necessary to address the issues. Typical Work Products 1. List of issues needing corrective actions Subpractices 1. Gather issues for analysis. Issues are collected from reviews and the execution of other processes. Examples of issues to be gathered include: · Issues discovered through performing verification and validation activities · Significant deviations in the project planning parameters from the estimates in the project plan · Commitments (either internal or external) that have not been satisfied · Significant changes in risk status · Data access, collection, privacy, or security issues · Stakeholder representation or involvement issues 2. Analyze issues to determine need for corrective action. Refer to the Project Planning process area for information about corrective action criteria. Corrective action is required when the issue, if left unresolved, may prevent the project from meeting its objectives. Issues are collected from reviews and the execution of other processes. Examples of issues to be gathered include: · Issues discovered through performing verification and validation activities · Significant deviations in the project planning parameters from the estimates in the project plan · Commitments (either internal or external) that have not been satisfied · Significant changes in risk status · Data access, collection, privacy, or security issues · Stakeholder representation or involvement issues | 1 - Coleta de dados sobre problemas identificados: Ao fim de cada Itereção dados sobre os problemas identificados devem ser documentados para posterior analise. 2 - Analise dos dados coletados: sobre Com base nos dados obtidos sobre os problemas identificados, deverá ser feita uma analise em cada item com o objetivo de classificar a gravidade dos problemas. | 1 - Sumário de problemas identificados: Descreve os problemas identificados a cada iteração. 2 - Sumário refinado: Classifica a gravidade dos problemas descritos no Sumário de problemas identificados.
PMC SP 2.2 | SP 2.2 Take Corrective Action Take corrective action on identified issues. Typical Work Products 1. Corrective action plan Subpractices 1. Determine and document the appropriate actions needed to address the identified issues. Refer to the Project Planning process area for more information about the project plan when re-planning is needed. Examples of potential actions include the following: · Modifying the statement of work · Modifying requirements · Revising estimates and plans · Renegotiating commitments · Adding resources · Changing processes · Revising project risks 2. Review and get agreement with relevant stakeholders on the actions to be taken. 3. Negotiate changes to internal and external commitments. | 1 - Indicar qual a ação corretiva que deverá ser aplicada a cada problema identificado | Ação de correção: Documento que indica qual a ação de correção que deve ser executada para cada tipo e gravidade de problema.
PMC SP 2.3 | SP 2.3 Manage Corrective Action Manage corrective actions to closure. Typical Work Products 1. Corrective action results Subpractices 1. Monitor corrective actions for completion. 2. Analyze results of corrective actions to determine the effectiveness of the corrective actions. 3. Determine and document appropriate actions to correct deviations from planned results for corrective actions. Lessons learned as a result of taking corrective action can be inputs to planning and risk management processes. | 1. Analisar eficácia das Ações Corretivas Tomadas | 1. Documento de Ações Corretivas Tomadas (qual ação foi tomada, quando esta ação foi tomada, e qual o resultado obtido antes e depois da tomada de ação)
Legenda Status - DEFINIÇÃO:
|  | TD | 0
|  | LD | 0
|  | PD | 0
|  | ND | 0
Note on C2: Alexandre Vasconcelos: Coloque aqui as atividades do processo modelado que evidenciam a aderência ao CMMI
Note on C16: * Processo escrito e aderente
Note on C17: * Existem pendências não muito críticas
Note on C18: * Existe uma parte da prática nao atendida pela definição
Note on C19: * Não está definido em nenhum lugar do processo ou não está aderente
Note on D2: Alexandre Vasconcelos: Coloque aqui os artefatos gerados pelo processo modelado que evidenciam a aderência ao CMMI
Note on E2: Alexandre Vasconcelos: A ser preenchido pelo Professor