## Graf. % Praticas Específicas
| REQM | PP | PMC | SAM | MA | PPQA | CM
ND | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD | 0 | 0 | 0 | 0 | 0 | 0 | 0
LD | 0 | 0 | 0 | 0 | 0 | 0 | 0
TD | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Práticas Genéricas
Práticas Genéricas |  | Campos | Áreas de Processo
GG 2 - INSTITUCIONALIZE A MANAGED PROCESS |  |  | REQM | PP | PMC | SAM | MA | PPQA | CM
(GP 2.1) | Establish an Organizational Policy | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.2) | Plan the Process | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.3) | Provide Resources | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.4) | Assign Responsibility | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.5) | Train People | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.6) | Manage Configurations | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.7) | Identify and Involve Relevant Stakeholders | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.8) | Monitor and Control the Process | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.9) | Objectively Evaluate Adherence | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 2.10) | Review Status with Higher Level Management | Descrição
Artefato direto
Status
Ação
Responsável
Data
GG 3 - INSTITUCIONALIZE A DEFINED PROCESS
(GP 3.1) | Establish a Defined Process | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 3.2) | Collect Improvement Information | Descrição
Artefato direto
Status
Ação
Responsável
Data
GG 4 - INSTITUCIONALIZE A QUANTITATIVELY MANAGED PROCESS
(GP 4.1) | Establish Quantitative Objectives for the Process | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 4.2) | Stabilize Subprocess Performance | Descrição
Artefato direto
Status
Ação
Responsável
Data
GG 5 - INSTITUCIONALIZE NA OPTIMIZING PROCESS
(GP 5.1) | Ensure Continuous Process Improvement | Descrição
Artefato direto
Status
Ação
Responsável
Data
(GP 5.2) | Correct Root Causes of Problems | Descrição
Artefato direto
Status
Ação
Responsável
Data
Legenda Status Institucionalização
|  |  |  | totalmente implementado | TI
|  |  |  | largamente implementado | LI
|  |  |  | parcialmente implementado | PI
|  |  |  | não implementado | NI
|  |  |  | prática alternativa | PA
|  |  | REQM | PP | PMC | SAM | MA | PPQA | CM
|  | TI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PA | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total de GP: | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C113: * Prática definida e institucionalizada
Note on C114: * Prática definida, institucionalizada tendo ainda algum ponto pendente não muito crítico
Note on C115: * Parte da prática não está institucionalizada
Note on C116: * Não Institucionalizado
Note on C117: * Feito de forma diferente do que está especificado no modelo
Note on F104: * Prática definida e institucionalizada
Note on F105: * Prática definida, institucionalizada tendo ainda algum ponto pendente não muito crítico
Note on F106: * Parte da prática não está institucionalizada
Note on F107: * Não Institucionalizado
Note on F108: * Feito de forma diferente do que está especificado no modelo

## REQM
REQM - Requirements Management |  | Processo da Organização
Cód. | Práticas Específicas | Sub-Processo | Atividade | Artefato Direto | Artefato Indireto | Status Def.
REQM SP 1.1 | SP 1.1 Obtain an Understanding of Requirements Develop an understanding with the requirements providers on the meaning of the requirements. As the project matures and requirements are derived, all activities or disciplines will receive requirements. To avoid requirements creep, criteria are established to designate appropriate channels, or official sources, from which to receive requirements. The receiving activities conduct analyses of the requirements with the requirements provider to ensure that a compatible, shared understanding is reached on the meaning of the requirements. The result of this analysis and dialog is an agreed-to set of requirements. Typical Work Products 1. Lists of criteria for distinguishing appropriate requirements providers 2. Criteria for evaluation and acceptance of requirements 3. Results of analyses against criteria 4. An agreed-to set of requirements Subpractices 1. Establish criteria for distinguishing appropriate requirements providers. 2. Establish objective criteria for the acceptance of requirements. Lack of acceptance criteria often results in inadequate verification, costly rework, or customer rejection. Examples of acceptance criteria include the following: · Clearly and properly stated · Complete · Consistent with each other · Uniquely identified · Appropriate to implement · Verifiable (testable) · Traceable 3. Analyze requirements to ensure that the established criteria are met. [PA146.IG101.SP101.SubP103] 4. Reach an understanding of the requirements with the requirements provider so the project participants can commit to them.
REQM SP 1.2 | SP 1.2 Obtain Commitment to Requirements Obtain commitment to the requirements from the project participants. Refer to the Project Monitoring and Control process area for more information about monitoring the commitments made. For Integrated Product and Process Development When integrated teams are formed, the project participants are the integrated teams and their members. Commitment to the requirement for interacting with other integrated teams is as important for each integrated team as its commitments to product and other project requirements. Whereas the previous specific practice dealt with reaching an understanding with the requirements providers, this specific practice deals with agreements and commitments among those who have to carry out the activities necessary to implement the requirements. Requirements evolve throughout the project, especially as described by the specific practices of the Requirements Development process area and the Technical Solution process area. As the requirements evolve, this specific practice ensures that project participants commit to the current, approved requirements and the resulting changes in project plans, activities, and work products. Typical Work Products 1. Requirements impact assessments 2. Documented commitments to requirements and requirements changes Subpractices 1. Assess the impact of requirements on existing commitments. The impact on the project participants should be evaluated when the requirements change or at the start of a new requirement. 2. Negotiate and record commitments. Changes to existing commitments should be negotiated before project participants commit to the requirement or requirement change.
REQM SP 1.3 | SP 1.3 Manage Requirements Changes Manage changes to the requirements as they evolve during the project. Refer to the Configuration Management process area for more information about maintaining and controlling the requirements baseline and on making the requirements and change data available to the project. During the project, requirements change for a variety of reasons. As needs change and as work proceeds, additional requirements are derived and changes may have to be made to the existing requirements. It is essential to manage these additions and changes efficiently and effectively. To effectively analyze the impact of the changes, it is necessary that the source of each requirement is known and the rationale for any change is documented. The project manager may, however, want to track appropriate measures of requirements volatility to judge whether new or revised controls are necessary. Typical Work Products 1. Requirements status 2. Requirements database 3. Requirements decision database Subpractices 1. Capture all requirements and requirements changes that are given to or generated by the project. 2. Maintain the requirements change history with the rationale for the changes. Maintaining the change history helps track requirements volatility. 3. Evaluate the impact of requirement changes from the standpoint of relevant stakeholders. 4. Make the requirements and change data available to the project.
REQM SP 1.4 | SP 1.4 Maintain Bidirectional Traceability of Requirements Maintain bidirectional traceability among the requirements and the project plans and work products. The intent of this specific practice is to maintain the bidirectional traceability of requirements for each level of product decomposition. When the requirements are managed well, traceability can be established from the source requirement to its lower level requirements and from the lower level requirements back to their source. Such bidirectional traceability helps determine that all source requirements have been completely addressed and that all lower level requirements can be traced to a valid source. Requirements traceability can also cover the relationships to other entities such as intermediate and final work products, changes in design documentation, test plans, and work tasks. The traceability should cover both the horizontal and vertical relationships, such as across interfaces. Traceability is particularly needed in conducting the impact assessment of requirements changes on the project plans, activities, and work products. Typical Work Products 1. Requirements traceability matrix 2. Requirements tracking system Subpractices 1. Maintain requirements traceability to ensure that the source of lower level (derived) requirements is documented. 2. Maintain requirements traceability from a requirement to its derived requirements as well as to its allocation of functions, objects, people, processes, and work products. 3. Maintain horizontal traceability from function to function and across interfaces. 4. Generate the requirements traceability matrix.
REQM SP 1.5 | SP 1.5 Identify Inconsistencies between Project Work and Requirements Identify inconsistencies between the project plans and work products and the requirements. Refer to the Project Monitoring and Control process area for more information about monitoring and controlling the project plans and work products for consistency with requirements and taking corrective actions when necessary. This specific practice finds the inconsistencies between the requirements and the project plans and work products and initiates the corrective action to fix them. Typical Work Products 1. Documentation of inconsistencies including sources, conditions, and rationale 2. Corrective actions Subpractices 1. Review the project's plans, activities, and work products for consistency with the requirements and the changes made to them. 2. Identify the source of the inconsistency and the rationale. 3. Identify changes that need to be made to the plans and work products resulting from changes to the requirements baseline. 4. Initiate corrective actions.
Legenda Status - DEFINIÇÃO:
|  |  | TD | 0
|  |  | LD | 0
|  |  | PD | 0
|  |  | ND | 0
Note on D11: * Processo escrito e aderente
Note on D12: * Existem pendências não muito críticas
Note on D13: * Existe uma parte da prática nao atendida pela definição
Note on D14: * Não está definido em nenhum lugar do processo ou não está aderente

## PP
PP - Project Planning |  | Processo da Organização
Cód. | Práticas Específicas | Processo | Atividade | Artefato Direto | Artefato Indireto | Status Def.
PP SP 1.1 | SP 1.1 Estimate the Scope of the Project Establish a top-level work breakdown structure (WBS) to estimate the scope of the project. The WBS evolves with the project. Initially a top-level WBS can serve to structure the initial estimating. The development of a WBS divides the overall project into an interconnected set of manageable components. The WBS is typically a product-oriented structure that provides a scheme for identifying and organizing the logical units of work to be managed, which are called "work packages." The WBS provides a reference and organizational mechanism for assigning effort, schedule, and responsibility and is used as the underlying framework to plan, organize, and control the work done on the project. Typical Work Products 1. Task descriptions 2. Work package descriptions 3. WBS Subpractices 1. Develop a WBS based on the product architecture. The WBS provides a scheme for organizing the project's work around the products that the work supports. The WBS should permit the identification of the following items: · Identified risks and their mitigation tasks · Tasks for deliverables and supporting activities · Tasks for skill and knowledge acquisition · Tasks for development of needed support plans, such as configuration management, quality assurance, and verification plans · Tasks for integration and management of non-developmental items 2. Identify the work packages in sufficient detail to specify estimates of project tasks, responsibilities, and schedule. The top-level WBS is intended to help in gauging the project work effort in terms of tasks and organizational roles and responsibilities. The amount of detail in the WBS at this more detailed level helps in developing realistic schedules, thereby minimizing the need for management reserve. 3. Identify work products (or components of work products) that will be externally acquired. Refer to the Supplier Agreement Management process area for more information about acquiring work products from sources external to the project. 4. Identify work products that will be reused.
PP SP 1.2 | SP 1.2 Establish Estimates of Work Product and Task Attributes Establish and maintain estimates of the attributes of the work products and tasks. Size is the primary input to many models used to estimate effort, cost, and schedule. The models may also be based on inputs such as connectivity, complexity, and structure. Examples of types of work products for which size estimates are made include the following: · Deliverable and nondeliverable work products . Documents · Operational and support software Examples of size measures include the following: · Number of functions · Function points · Source lines of code · Number of classes and objects · Number of requirements · Number of interfaces · Number of pages · Number of inputs and outputs · Number of technical risk items · Volume of data The estimates should be consistent with project requirements to determine the project's effort, cost, and schedule. A relative level of difficulty or complexity should be assigned for each size attribute. Typical Work Products 1. Technical approach 2. Size and complexity of tasks and work products 3. Estimating models 4. Attribute estimates Subpractices 1. Determine the technical approach for the project. The technical approach defines a top-level strategy for development of the products. It includes decisions on architectural features, such as distributed or client server; state-of-the-art or established technologies to be applied, such as robotics, composite materials, or artificial intelligence; and breadth of the functionality expected in the final products, such as safety, security, and ergonomics. 2. Use appropriate methods to determine the attributes of the work products and tasks that will be used to estimate the resource requirements. Methods for determining size and complexity should be based on validated models or historical data. The methods for determining attributes evolve as our understanding of the relationship of product characteristics to attributes increases. Examples of current methods include the following: · Number of logic gates for integrated circuit design · Lines of code or function points for software · Number/complexity of requirements for systems engineering · Number of square feet for standard-specified residential homes 3. Estimate the attributes of the work products and tasks. 4. Estimate, as appropriate, the labor, machinery, materials, and methods that will be required by the project.
PP SP 1.3 | SP 1.3 Define Project Life Cycle Define the project life-cycle phases upon which to scope the planning effort. The determination of a project's life-cycle phases provides for planned periods of evaluation and decision making. These are normally defined to support logical decision points at which significant commitments are made concerning resources and technical approach. Such points provide planned events at which project course corrections and determinations of future scope and cost can be made. For Software Engineering The determination of project phases for software typically includes selection and refinement of a software development model to address interdependencies and appropriate sequencing of software project activities. For Systems Engineering Identify the major product phase (e.g., concept exploration, development, etc.) for the current state of the product, expected future phases, and the relationships and effects among phases. Adjust planning parameters to account for relationships and effects among phases. The project life cycle consists of phases that need to be defined depending on the scope of requirements, the estimates for project resources, and the nature of the project. Larger projects may contain multiple phases, such as concept exploration, development, production, operations, and disposal. Within these phases, subphases may be needed. A development phase may include subphases such as requirements analysis, design, fabrication, integration, and verification. Depending on the strategy for development, there may be intermediate phases for the creation of prototypes, increments of capability, or spiral model cycles. Understanding the project life cycle is crucial in determining the scope of the planning effort and the timing of the initial planning, as well as the timing and criteria (critical milestones) for re-planning. Typical Work Products 1. Project life-cycle phases
PP SP 1.4 | SP 1.4 Determine Estimates of Effort and Cost Estimate the project effort and cost for the work products and tasks based on estimation rationale. Estimates of effort and cost are generally based on the results of analysis using models or historical data applied to size, activities, and other planning parameters. Confidence in these estimates is based on the rationale for the selected model and the nature of the data. There may be occasions where the available historical data does not apply, such as where efforts are unprecedented or where the type of task does not fit available models. An effort is unprecedented (to some degree) if a similar product or component has never been built. An effort may also be unprecedented if the development group has never built such a product or component. Unprecedented efforts are more risky, require more research to develop reasonable bases of estimate, and require more management reserve. The uniqueness of the project must be documented when using these models to ensure a common understanding of any assumptions made in the initial planning stages. Typical Work Products 1. Estimation rationale 2. Project effort estimates 3. Project cost estimates Subpractices 1. Collect the models or historical data that will be used to transform the attributes of the work products and tasks into estimates of the labor hours and cost. For Software Engineering Within the software-engineering area, many parametric models have been developed to aid in estimating cost and schedule. The use of these models as the sole source of estimation is not recommended as these models are based on historical project data that may or may not be pertinent to your project. Multiple models and/or methods may be used to ensure a high level of confidence in the estimate. Historical data include the cost, effort, and schedule data from previously executed projects, plus appropriate scaling data to account for differing sizes and complexity. 2. Include supporting infrastructure needs when estimating effort and cost. The support infrastructure includes items needed from a development and sustainment perspective for the product. For Software Engineering Consider critical computer resources in the host environment, in the test environment, in the target environment, or in any combination of these. Computer resource estimation typically includes the following: · identifying the critical computer resources for the software project and · basing estimates of critical computer resources on allocated requirements For Software Engineering Examples of critical computer resources include the following: · Memory, disk, and network capacity · Processor power · Communications channel capacity · Workstation power · Peripheral capacity For Software Engineering Examples of software-engineering facilities include the following: · Host computers, peripherals, and networks · Software test computers and peripherals · Target computer environment software · Software-engineering environment (i.e., software tools) 3. Estimate effort and cost using models and/or historical data. Effort and cost inputs used for estimating typically include the following: · Judgmental estimates provided by an expert or group of experts (e.g., Delphi Method) · Risks, including the extent to which the effort is unprecedented · Critical competencies and roles needed to perform the work · Product and product-component requirements · Technical approach · WBS · Size estimates of work products and anticipated changes · Cost of externally acquired work products · Selected project life-cycle model and processes · Life-cycle cost estimates · Capability of tools provided in engineering environment · Skill levels of managers and staff needed to perform the work · Knowledge, skill, and training needs · Facilities needed (e.g., office and meeting space and workstations) · Engineering facilities needed · Capability of manufacturing process(es) · Travel · Level of security required for tasks, work products, hardware, software, personnel, and work environment · Service-level agreements for call centers and warranty work · Direct labor and overhead
PP SP 2.1 | SP 2.1 Establish the Budget and Schedule Establish and maintain the project's budget and schedule. The project's budget and schedule are based on the developed estimates and ensure that budget allocation, task complexity, and task dependencies are appropriately addressed. Event-driven, resource-limited schedules have proven to be effective in dealing with project risk. Identifying accomplishments to be demonstrated before initiation of the event provides some flexibility in the timing of the event, a common understanding of what is expected, a better vision of the state of the project, and a more accurate status of the project's tasks. Typical Work Products 1. Project schedules 2. Schedule dependencies 3. Project budget Subpractices 1. Identify major milestones. Milestones are often imposed to ensure completion of certain deliverables by the milestone. Milestones can be event based or calendar based. If calendar based, once milestone dates have been agreed upon, it is often very difficult to change them. 2. Identify schedule assumptions. When schedules are initially developed, it is common to make assumptions about the duration of certain activities. These assumptions are frequently made on items for which little if any estimation data is available. Identifying these assumptions provides insight into the level of confidence (uncertainties) in the overall schedule. 3. Identify constraints. Factors that limit the flexibility of management options need to be identified as early as possible. The examination of the attributes of the work products and tasks will often surface these issues. Such attributes can include task duration, resources, inputs, and outputs. 4. Identify task dependencies. Typically, the tasks for a project can be accomplished in some ordered sequence that will minimize the duration of the project. This involves the identification of predecessor and successor tasks to determine the optimal ordering. Examples of tools that can help determine an optimal ordering of task activities include the following: · Critical Path Method (CPM) · Program Evaluation and Review Technique (PERT) · Resource-limited scheduling 5. Define the budget and schedule. Establishing and maintaining the project's budget and schedule typically includes the following: · Defining the committed or expected availability of resources and facilities · Determining time phasing of activities · Determining a breakout of subordinate schedules · Defining the dependencies between the activities (predecessor or successor relationships) · Defining the schedule activities and milestones to support accuracy in progress measurement · Identifying milestones for delivery of products to the customer · Defining activities of appropriate duration · Defining milestones of appropriate time separation · Defining a management reserve based on the confidence level in meeting the schedule and budget · Using appropriate historical data to verify the schedule · Defining incremental funding requirements · Documenting project assumptions and rationale 6. Establish corrective action criteria. Criteria are established for determining what constitutes a significant deviation from the project plan. A basis for gauging issues and problems is necessary to determine when a corrective action should be taken. The corrective actions may require re-planning, which may include revising the original plan, establishing new agreements, or including mitigation activities within the current plan.
PP SP 2.2 | SP 2.2 Identify Project Risks Identify and analyze project risks. Refer to the Risk Management process area for more information about risk management activities. Refer to the Monitor Project Risks specific practice in the Project Monitoring and Control process area for more information about risk monitoring activities. Risks are identified or discovered and analyzed to support project planning. This specific practice should be extended to all the plans that affect the project to ensure that the appropriate interfacing is taking place between all relevant stakeholders on identified risks. Project planning risk identification and analysis typically include the following: · Identifying risks · Analyzing the risks to determine the impact, probability of occurrence, and time frame in which problems are likely to occur · Prioritizing risks Typical Work Products 1. Identified risks 2. Risk impacts and probability of occurrence 3. Risk priorities Subpractices 1. Identify risks. The identification of risks involves the identification of potential issues, hazards, threats, vulnerabilities, etc. that could negatively affect work efforts and plans. Risks must be identified and described in an understandable way before they can be analyzed. When identifying risks, it is good to use a standard method for defining risks. Risk identification and analysis tools may be used to help identify possible problems. Examples of risk identification and analysis tools include the following: · Risk taxonomies · Risk assessments · Checklists · Structured interviews · Brainstorming · Performance models · Cost models · Network analysis · Quality factor analysis 2. Document the risks. 3. Review and obtain agreement with relevant stakeholders on the completeness and correctness of the documented risks. 4. Revise the risks as appropriate. Examples of when identified risks may need to be revised include the following: · When new risk is identified · When risks become problems · When risks are retired · When project circumstances change significantly
PP SP 2.3 | SP 2.3 Plan for Data Management Plan for the management of project data. For Integrated Product and Process Development When integrated teams are formed, project data includes data developed and used solely within a particular team as well as data applicable across integrated team boundaries if there are multiple integrated teams. Data are the various forms of documentation required to support a program in all of its areas (e.g., administration, engineering, configuration management, financial, logistics, quality, safety, manufacturing, and procurement). The data may take any form (e.g., reports, manuals, notebooks, charts, drawings, specifications, files, or correspondence). The data may exist in any medium (e.g., printed or drawn on various materials, photographs, electronic, or multimedia). Data may be deliverable (e.g., items identified by a program's contract data requirements) or data may be nondeliverable (e.g., informal data, trade studies and analyses, internal meeting minutes, internal design review documentation, lessons learned, and action items). Distribution may take many forms, including electronic transmission. The data requirements for the project should be established for both the data items to be created and their content and form, based on a common or standard set of data requirements. Uniform content and format requirements for data items facilitate understanding of data content and help with consistent management of the data resources. The reason for collecting each document should be clear. This task includes the analysis and verification of project deliverables and nondeliverables, contract and noncontract data requirements, and customer-supplied data. Often, data is collected with no clear understanding of how it will be used. Data is costly and should be collected only when needed. Typical Work Products 1. Data management plan 2. Master list of managed data 3. Data content and format description 4. Data requirements lists for acquirers and for suppliers 5. Privacy requirements 6. Security requirements 7. Security procedures 8. Mechanism for data retrieval, reproduction, and distribution 9. Schedule for collection of project data . 10. Listing of project data to be collected Subpractices 1. Establish requirements and procedures to ensure privacy and security of the data. Not everyone will have the need or clearance necessary to access the project data. Procedures must be established to identify who has access to what data as well as when they have access to the data. 2. Establish a mechanism to archive data and to access archived data. Accessed information should be in an understandable form (e.g., electronic or computer output from a database) or represented as originally generated. 3. Determine the project data to be identified, collected, and distributed.
PP SP 2.4 | SP 2.4 Plan for Project Resources Plan for necessary resources to perform the project. For Integrated Product and Process Development When integrated teams are formed, planning for project resources has to consider staffing of the integrated teams. Defining project resources (labor, machinery/equipment, materials, and methods) and quantities needed to perform project activities builds on the initial estimates and provides additional information that can be applied to expand the WBS used to manage the project. The top-level WBS developed earlier as an estimation mechanism is typically expanded by decomposing these top levels into work packages that represent singular work units that can be separately assigned, performed, and tracked. This subdivision is done to distribute management responsibility and provide better management control. Each work package or work product in the WBS should be assigned a unique identifier (e.g., number) to permit tracking. A WBS may be based on requirements, activities, work products, or a combination of these items. A dictionary that describes the work for each work package in the WBS should accompany the work breakdown structure. Typical Work Products 1. WBS work packages 2. WBS task dictionary 3. Staffing requirements based on project size and scope 4. Critical facilities/equipment list 5. Process/workflow definitions and diagrams 6. Program administration requirements list Subpractices 1. Determine process requirements. The processes used to manage a project must be identified, defined, and coordinated with all the relevant stakeholders to ensure efficient operations during project execution. 2. Determine staffing requirements. The staffing of a project depends on the decomposition of the project requirements into tasks, roles, and responsibilities for accomplishing the project requirements as laid out within the work packages of the WBS. Staffing requirements must consider the knowledge and skills required for each of the identified positions, as defined in the Plan for Needed Knowledge and Skills specific practice. 3. Determine facilities, equipment, and component requirements. Most projects are unique in some sense and require some set of unique assets to accomplish the objectives of the project. The determination and acquisition of these assets in a timely manner are crucial to project success. Lead-time items need to be identified early to determine how they will be addressed. Even when the required assets are not unique, compiling a list of all of the facilities, equipment, and parts (e.g., number of computers for the personnel working on the project, software applications, office space, etc.) provides insight into aspects of the scope of an effort that are often overlooked.
PP SP 2.5 | SP 2.5 Plan for Needed Knowledge and Skills Plan for knowledge and skills needed to perform the project. Refer to the Organizational Training process area for more information about knowledge and skills information to be incorporated into the project plan. Knowledge delivery to projects involves both training of project personnel and acquisition of knowledge from outside sources. Staffing requirements are dependent on the knowledge and skills available to support the execution of the project. Typical Work Products 1. Inventory of skill needs 2. Staffing and new hire plans 3. Databases (e.g., skills and training) Subpractices 1. Identify the knowledge and skills needed to perform the project. 2. Assess the knowledge and skills available. 3. Select mechanisms for providing needed knowledge and skills. Example mechanisms include the following: · In-house training (both organizational and project) · External training · Staffing and new hires · External skill acquisition The choice of in-house training or external outsourcing for the needed knowledge and skills is determined by the availability of training expertise, the project's schedule, and business objectives. 4. Incorporate selected mechanisms in the project plan.
PP SP 2.6 | SP 2.6 Plan Stakeholder Involvement Plan the involvement of identified stakeholders. For Integrated Product and Process Development When integrated teams are formed, stakeholder involvement needs to be planned down to the integrated team level. Stakeholders are identified from all phases of the project life cycle by identifying the type of people and functions needing representation in the project and describing their relevance and the degree of interaction for specific project activities. A two-dimensional matrix with stakeholders along one axis and project activities along the other axis is a convenient format for accomplishing this identification. Relevance of the stakeholder to the activity in a particular project phase and the amount of interaction expected would be shown at the intersection of the project phase activity axis and the stakeholder axis. For the inputs of stakeholders to be useful, careful selection of relevant stakeholders is necessary. For each major activity, identify the stakeholders that are affected by the activity and those who have expertise that is needed to conduct the activity. This list of relevant stakeholders will probably change as the project moves through the phases of the project life cycle. It is important, however, to ensure that relevant stakeholders in the later phases of the life cycle have early input to requirements and design decisions that affect them. Examples of the type of material that should be included in a plan for stakeholder interaction include the following: · List of all relevant stakeholders · Rationale for stakeholder involvement · Roles and responsibilities of the relevant stakeholders with respect to the project, by project life-cycle phase · Relationships between stakeholders · Relative importance of the stakeholder to success of the project, by project life-cycle phase · Resources (e.g., training, materials, time, funding) needed to ensure stakeholder interaction · Schedule for phasing of stakeholder interaction Conduct of this specific practice relies on shared or exchanged information with the previous Plan for Needed Knowledge and Skills specific practice. Typical Work Products 1. Stakeholder involvement plan
PP SP 2.7 | SP 2.7 Establish the Project Plan Establish and maintain the overall project plan content. For Systems Engineering Systems-engineering planning details the work activities and work products of the integrated technical effort across the project. For Systems Engineering Examples of plans that have been used in the U.S. Department of Defense community include the following: · Integrated Master Plan - an event-driven plan that documents significant accomplishments with pass/fail criteria for both business and technical elements of the project and ties each accomplishment to a key program event. · Integrated Master Schedule - an integrated and networked multi-layered schedule of program tasks required to complete the work effort documented in a related Integrated Master Plan. · Systems-Engineering Management Plan - a plan that details the integrated technical effort across the project. · Systems-Engineering Master Schedule - an event-based schedule that contains a compilation of key technical accomplishments, each with measurable criteria, requiring successful completion to pass identified events. · Systems-Engineering Detailed Schedule - a detailed, time-dependent, task-oriented schedule that associates specific dates and milestones with the Systems-Engineering Master Schedule. For Software Engineering For software, the planning document is often referred to as one of the following: · Software development plan · Software project plan · Software plan A documented plan that addresses all relevant planning items is necessary to achieve the mutual understanding, commitment, and performance of individuals, groups, and organizations that must execute or support the plans. The plan generated for the project defines all aspects of the effort, tying together in a logical manner: project life-cycle considerations; technical and management tasks; budgets and schedules; milestones; data management, risk identification, resource and skill requirements; and stakeholder identification and interaction. Infrastructure descriptions include responsibility and authority relationships for project staff, management, and support organizations. Typical Work Products 1. Overall project plan
PP SP 3.1 | SP 3.1 Review Plans that Affect the Project Review all plans that affect the project to understand project commitments. For Integrated Product and Process Development When integrated teams are formed, their integrated work plans are among the plans to review. Plans developed within other process areas will typically contain information similar to that called for in the overall project plan. These plans may provide additional detailed guidance and should be compatible with and support the overall project plan to indicate who has the authority, responsibility, accountability, and control. All plans that affect the project should be reviewed to ensure a common understanding of the scope, objectives, roles, and relationships that are required for the project to be successful. Many of these plans are described by the Plan the Process generic practice in each of the process areas. Typical Work Products 1. Record of the reviews of plans that affect the project
PP SP 3.2 | SP 3.2 Reconcile Work and Resource Levels Reconcile the project plan to reflect available and estimated resources. For Integrated Product and Process Development When integrated teams are formed, special attention needs to be paid to resource commitments in circumstances of distributed integrated teams and when people are on multiple integrated teams in one or many projects. To obtain commitment from relevant stakeholders, it is important to reconcile any differences between the estimates and the available resources. Reconciliation is typically accomplished by lowering or deferring technical performance requirements, negotiating more resources, finding ways to increase productivity, outsourcing, adjusting the staff skill mix, or revising all plans that affect the project or schedules. Typical Work Products 1. Revised methods and corresponding estimating parameters (e.g., better tools, use of off-the-shelf components) 2. Renegotiated budgets 3. Revised schedules 4. Revised requirements list 5. Renegotiated stakeholder agreements
PP SP 3.3 | SP 3.3 Obtain Plan Commitment Obtain commitment from relevant stakeholders responsible for performing and supporting plan execution. For Integrated Product and Process Development When integrated teams are formed, the integrated team plans will need buy-in from the team members, the interfacing teams, the project, and the process owners of the standard processes that team has selected for tailored application. Obtaining commitment involves interaction among all relevant stakeholders both internal and external to the project. The individual or group making a commitment should have confidence that the work can be performed within cost, schedule, and performance constraints. Often, a provisional commitment is adequate to allow the effort to begin and to permit research to be performed to increase confidence to the appropriate level needed to obtain a full commitment. Typical Work Products 1. Documented requests for commitments 2. Documented commitments Subpractices 1. Identify needed support and negotiate commitments with relevant stakeholders. The WBS can be used as a checklist for ensuring that commitments are obtained for all tasks. The plan for stakeholder interaction should identify all parties from whom commitment should be obtained. 2. Document all organizational commitments, both full and provisional, ensuring appropriate level of signatories. Commitments must be documented to ensure a consistent mutual understanding as well as for tracking and maintenance. Provisional commitments should be accompanied by a description of the risks associated with the relationship. 3. Review internal commitments with senior management as appropriate. 4. Review external commitments with senior management as appropriate. Management may have the necessary insight and authority to reduce risks associated with external commitments. 5. Identify commitments on interfaces between elements in the project, and with other projects and organizational units, so they can be monitored. Well-defined interface specifications form the basis for commitments.
Legenda Status - DEFINIÇÃO:
|  |  | TD | 0
|  |  | LD | 0
|  |  | PD | 0
|  |  | ND | 0
Note on D20: * Processo escrito e aderente
Note on D21: * Existem pendências não muito críticas
Note on D22: * Existe uma parte da prática nao atendida pela definição
Note on D23: * Não está definido em nenhum lugar do processo ou não está aderente

## PMC
PMC - Project Monitoring and Control |  | Processo da Organização
Cód. | Práticas Específicas | Processo | Atividade | Artefato Direto | Artefato Indireto | Status Def.
PMC SP 1.1 | SP 1.1 Monitor Project Planning Parameters Monitor the actual values of the project planning parameters against the project plan. Project planning parameters constitute typical indicators of project progress and performance and include attributes of work products and tasks, cost, effort, and schedule. Attributes of the work products and tasks include such items as size, complexity, weight, form, fit, or function. Monitoring typically involves measuring the actual values of project planning parameters, comparing actual values to the estimates in the plan, and identifying significant deviations. Recording actual values of the project planning parameters includes recording associated contextual information to help understand the measures. An analysis of the impact that significant deviations have on determining what corrective actions to take is handled in the second specific goal and its specific practices in this process area. Typical Work Products 1. Records of project performance 2. Records of significant deviations Subpractices 1. Monitor progress against the schedule. Progress monitoring typically includes the following: · Periodically measuring the actual completion of activities and milestones · Comparing actual completion of activities and milestones against the schedule documented in the project plan · Identifying significant deviations from the schedule estimates in the project plan 2. Monitor the project's cost and expended effort. Effort and cost monitoring typically includes the following: · Periodically measuring the actual effort and cost expended and staff assigned · Comparing actual effort, costs, staffing, and training to the estimates and budgets documented in the project plan · Identifying significant deviations from the budgets in the project plan 3. Monitor the attributes of the work products and tasks. Refer to the Project Planning process area for information about the attributes of work products and tasks. Monitoring the attributes of the work products and tasks typically includes the following: · Periodically measuring the actual attributes of the work products and tasks, such as size or complexity (and the changes to the attributes) · Comparing the actual attributes of the work products and tasks (and the changes to the attributes) to the estimates documented in the project plan · Identifying significant deviations from the estimates in the project plan 4. Monitor resources provided and used. Refer to the Project Planning process area for information about planned resources. For Software Engineering Examples of software-engineering resources include the following: · Host computers and peripherals · Networks · Software test computers and peripherals · Target computer environment software · Software-engineering environment (e.g., software tools) Examples of resources include: · Physical facilities · Computers, peripherals, and software used in design, manufacturing, testing and operation · Networks · Security environment · Project staff · Processes 5. Monitor the knowledge and skills of project personnel. Refer to the Project Planning process area for information about planning for knowledge and skills needed to perform the project. Monitoring the knowledge and skills of the project personnel typically includes the following: · Periodically measuring the acquisition of knowledge and skills by project personnel · Comparing the actual training obtained to that documented in the project plan · Identifying significant deviations from the estimates in the project plan 6. Document the significant deviations in the project planning parameters.
PMC SP 1.2 | SP 1.2 Monitor Commitments Monitor commitments against those identified in the project plan. Typical Work Products 1. Records of commitment reviews Subpractices 1. Regularly review commitments (both external and internal). 2. Identify commitments that have not been satisfied or which are at significant risk of not being satisfied. 3. Document the results of the commitment reviews.
PMC SP 1.3 | SP 1.3 Monitor Project Risks Monitor risks against those identified in the project plan. Refer to the Project Planning process area for more information about identifying project risks. Refer to the Risk Management process area for more information about risk management activities. Typical Work Products 1. Records of project risk monitoring Subpractices 1. Periodically review the documentation of the risks in the context of the project's current status and circumstances. 2. Revise the documentation of the risks, as additional information becomes available, to incorporate changes. 3. Communicate risk status to relevant stakeholders. Examples of risk status include the following: · A change in the probability that the risk occurs · A change in risk priority
PMC SP 1.4 | SP 1.4 Monitor Data Management Monitor the management of project data against the project plan. Refer to the Plan for Data Management specific practice in the Project Planning process area for more information about identifying the types of data that should be managed and how to plan for their management. Once the plans for the management of project data are made, the management of that data must be monitored to ensure that those plans are accomplished. Typical Work Products 1. Records of data management Subpractices 1. Periodically review data management activities against their description in the project plan. 2. Identify and document significant issues and their impacts. 3. Document the results of data management activity reviews.
PMC SP 1.5 | SP 1.5 Monitor Stakeholder Involvement Monitor stakeholder involvement against the project plan. Refer to the Plan Stakeholder Involvement specific practice in the Project Planning process area for more information on identifying relevant stakeholders and planning the appropriate involvement with them. Once the stakeholders are identified and the extent of their involvement within the project is specified in project planning, that involvement must be monitored to ensure that the appropriate interactions are occurring. Typical Work Products 1. Records of stakeholder involvement Subpractices 1. Periodically review the status of stakeholder involvement. 2. Identify and document significant issues and their impacts. 3. Document the results of the stakeholder involvement status reviews.
PMC SP 1.6 | SP 1.6 Conduct Progress Reviews Periodically review the project's progress, performance, and issues. Progress reviews are reviews on the project to keep stakeholders informed. These project reviews can be informal reviews and may not be specified explicitly in the project plans. Examples of these reviews include the following: · Reviews with staff · Reviews with project engineers and support · Reviews with management Typical Work Products 1. Documented project review results Subpractices 1. Regularly communicate status on assigned activities and work products to relevant stakeholders. Managers, staff members, customers, end users, suppliers, and other relevant stakeholders within the organization are included in the reviews as appropriate. 2. Review the results of collecting and analyzing measures for controlling the project. Refer to the Measurement and Analysis process area for more information about the process for measuring and analyzing project performance data. 3. Identify and document significant issues and deviations from the plan. 4. Document change requests and problems identified in any of the work products and processes. Refer to the Configuration Management process area for more information about how changes are managed. 5. Document the results of the reviews. 6. Track change requests and problem reports to closure.
PMC SP 1.7 | SP 1.7 Conduct Milestone Reviews Review the accomplishments and results of the project at selected project milestones. Refer to the Project Planning process area for more information about milestone planning. Milestone reviews are planned during project planning and are typically formal reviews. Typical Work Products 1.Documented milestone review results Subpractices 1. Conduct reviews at meaningful points in the project's schedule, such as the completion of selected stages, with relevant stakeholders. Managers, staff members, customers, end users, suppliers, and other relevant stakeholders within the organization are included in the milestone reviews as appropriate. 2. Review the commitments, plan, status, and risks of the project. 3. Identify and document significant issues and their impacts. 4. Document the results of the review, action items, and decisions. 5. Track action items to closure.
PMC SP 2.1 | SP 2.1 Analyze Issues Collect and analyze the issues and determine the corrective actions necessary to address the issues. Typical Work Products 1. List of issues needing corrective actions Subpractices 1. Gather issues for analysis. Issues are collected from reviews and the execution of other processes. Examples of issues to be gathered include: · Issues discovered through performing verification and validation activities · Significant deviations in the project planning parameters from the estimates in the project plan · Commitments (either internal or external) that have not been satisfied · Significant changes in risk status · Data access, collection, privacy, or security issues · Stakeholder representation or involvement issues 2. Analyze issues to determine need for corrective action. Refer to the Project Planning process area for information about corrective action criteria. Corrective action is required when the issue, if left unresolved, may prevent the project from meeting its objectives. Issues are collected from reviews and the execution of other processes. Examples of issues to be gathered include: · Issues discovered through performing verification and validation activities · Significant deviations in the project planning parameters from the estimates in the project plan · Commitments (either internal or external) that have not been satisfied · Significant changes in risk status · Data access, collection, privacy, or security issues · Stakeholder representation or involvement issues
PMC SP 2.2 | SP 2.2 Take Corrective Action Take corrective action on identified issues. Typical Work Products 1. Corrective action plan Subpractices 1. Determine and document the appropriate actions needed to address the identified issues. Refer to the Project Planning process area for more information about the project plan when re-planning is needed. Examples of potential actions include the following: · Modifying the statement of work · Modifying requirements · Revising estimates and plans · Renegotiating commitments · Adding resources · Changing processes · Revising project risks 2. Review and get agreement with relevant stakeholders on the actions to be taken. 3. Negotiate changes to internal and external commitments.
PMC SP 2.3 | SP 2.3 Manage Corrective Action Manage corrective actions to closure. Typical Work Products 1. Corrective action results Subpractices 1. Monitor corrective actions for completion. 2. Analyze results of corrective actions to determine the effectiveness of the corrective actions. 3. Determine and document appropriate actions to correct deviations from planned results for corrective actions. Lessons learned as a result of taking corrective action can be inputs to planning and risk management processes.
Legenda Status - DEFINIÇÃO:
|  |  | TD | 0
|  |  | LD | 0
|  |  | PD | 0
|  |  | ND | 0
Note on D16: * Processo escrito e aderente
Note on D17: * Existem pendências não muito críticas
Note on D18: * Existe uma parte da prática nao atendida pela definição
Note on D19: * Não está definido em nenhum lugar do processo ou não está aderente

## SAM
SAM - Supplier Agreement Management |  | Processo da Organização
Cód. | Práticas Específicas | Processo | Atividade | Artefato Direto | Artefato Indireto | Status Def.
SAM SP 1.1 | SP 1.1 Determine Acquisition Type Determine the type of acquisition for each product or product component to be acquired. Refer to the Technical Solution process area for more information about identifying the products and product components to be acquired. There are many different types of acquisition that can be used to acquire products and product components that will be used by the project. Examples of types of acquisition include the following: · Purchasing commercial off-the-shelf (COTS) products · Obtaining products through a contractual agreement · Obtaining products from an in-house vendor · Obtaining products from the customer · Combining some of the above (e.g., contracting for a modification to a COTS product or having another part of the business enterprise co-develop products with an external supplier) Typical Work Products 1. List of the acquisition types that will be used for all products and product components to be acquired
SAM SP 1.2 | SP 1.2 Select Suppliers Select suppliers based on an evaluation of their ability to meet the specified requirements and established criteria. Refer to the Decision Analysis and Resolution process area for more information about formal evaluation approaches that can be used to select suppliers. Refer to the Requirements Management process area for more information about specified requirements. Criteria should be established to address factors that are important to the project. Examples of factors include the following: · Geographical location of the supplier · Supplier's performance records on similar work · Engineering capabilities · Staff and facilities available to perform the work · Prior experience in similar applications Typical Work Products 1. List of candidate suppliers 2. Preferred supplier list 3. Rationale for selection of suppliers 4. Advantages and disadvantages of candidate suppliers 5. Evaluation criteria 6. Solicitation materials and requirements Subpractices 1. Establish and document criteria for evaluating potential suppliers. 2. Identify potential suppliers and distribute solicitation material and requirements to them. 3. Evaluate proposals according to evaluation criteria. 4. Evaluate risks associated with each proposed supplier. Refer to the Risk Management process area for more information about evaluating project risks. 5. Evaluate proposed suppliers' ability to perform the work. Examples of methods to evaluate the proposed supplier's ability to perform the work include the following: · Evaluation of prior experience in similar applications · Evaluation of prior performance on similar work · Evaluation of management capabilities · Capability evaluations · Evaluation of staff available to perform the work · Evaluation of available facilities and resources · Evaluation of the project's ability to work with the proposed supplier 6. Select the supplier.
SAM SP 1.3 | SP 1.3 Establish Supplier Agreements Establish and maintain formal agreements with the supplier. For Integrated Product and Process Development When integrated teams are formed, team membership should be negotiated with suppliers and incorporated into the agreement. The agreement should identify any integrated decision making, reporting requirements (business and technical), and trade studies requiring supplier involvement. The supplier efforts should be orchestrated to support the IPPD efforts undertaken by the acquirer. A formal agreement is any legal agreement between the organization (representing the project) and the supplier. This agreement may be a contract, a license, or a memorandum of agreement. Typical Work Products 1. Statements of work 2. Contracts 3. Memoranda of agreement 4.Licensing agreement Subpractices 1. Revise the requirements to be fulfilled by the supplier to reflect negotiations with the supplier when necessary. Refer to the Requirements Development process area for more information about revising requirements. Refer to the Requirements Management process area for more information about managing changes to requirements. 2. Document what the project will provide to the supplier. Include the following: · Project-furnished facilities · Documentation · Services 3. Document the supplier agreement. The supplier agreement should include a statement of work, a specification, terms and conditions, a list of deliverables, a schedule, a budget, and a defined acceptance process. This subpractice typically includes the following: · Establishing the statement of work, specification, terms and conditions, list of deliverables, schedule, budget, and acceptance process · Identifying who from the project and supplier are responsible and authorized to make changes to the supplier agreement · Identifying how requirements changes and changes to the supplier agreement are determined, communicated, and addressed · Identifying standards and procedures that will be followed · Identifying critical dependencies between the project and the supplier · Identifying the type and depth of project oversight of the supplier, procedures, and evaluation criteria to be used in monitoring supplier performance · Identifying the types of reviews that will be conducted with the supplier · Identifying the supplier's responsibilities for ongoing maintenance and support of the acquired products · Identifying warranty, ownership, and usage rights for the acquired products · Identifying acceptance criteria 4. Ensure all parties to the agreement understand and agree to all requirements before implementing the agreement. 5. Revise the supplier agreement as necessary. 6. Revise the project's plans and commitments as necessary to reflect the supplier agreement. Refer to the Project Monitoring and Control process area for more information about revising the project plan.
SAM SP 2.1 | SP 2.1 Review COTS Products Review candidate COTS products to ensure they satisfy the specified requirements that are covered under a supplier agreement. In the event that COTS products are desired, care in evaluating and selecting these products and the vendor may be critical to the project. Typical Work Products 1. Trade studies 2. Price lists 3. Evaluation criteria 4. Supplier performance reports 5. Reviews of COTS products Subpractices 1. Develop criteria for evaluating COTS products. 2. Evaluate candidate COTS products against the associated requirements and criteria. Refer to the Requirements Development process area for more information about the requirements that will be used to evaluate candidate products. These requirements address the following: · Functionality, performance, quality, and reliability · Terms and conditions of warranties for the products · Risk · Suppliers' responsibilities for ongoing maintenance and support of the products 3. Evaluate the impact of candidate COTS products on the project's plans and commitments. Evaluate according to the following: · Cost of the COTS products · Cost and effort to incorporate the COTS products into the project · Security requirements · Benefits and impacts that may result from future product releases Future product releases may provide additional features that support planned or anticipated enhancements for the project, but may also result in the supplier withdrawing support of the version for the product that is acquired by the project. 4. Assess the suppliers' performance and ability to deliver. 5. Identify risks associated with the selected COTS product and the supplier agreement. Refer to the Project Planning process area for more information about identifying project risks. Refer to the Risk Management process area for more information about identifying project risks. ] 6. Select the COTS product to be acquired. In some cases, selection of COTS products may require a supplier agreement in addition to the agreements in the product's license. Examples of agreements with COTS suppliers include the following: · Discounts for large quantity purchases · Coverage of relevant stakeholders under the licensing agreement, including project suppliers, team members, and the project's customer · Plans for future enhancements · On-site support, such as responses to queries and problem reports · Additional capabilities that are not in the product · Maintenance support, including support after the product is withdrawn from general availability 7. Plan for the maintenance of the COTS product.
SAM SP 2.2 | SP 2.2 Execute the Supplier Agreement Perform activities with the supplier as specified in the supplier agreement. Refer to the Project Monitoring and Control process area for more information about monitoring projects and taking corrective action. Typical Work Products 1. Supplier progress reports and performance measures 2. Supplier review materials and reports 3. Action items tracked to closure 4. Documentation of product and document deliveries Subpractices 1. Monitor supplier progress and performance (schedule, effort, cost, and technical performance) as defined in the supplier agreement. 2. Monitor selected supplier processes and take corrective action when necessary. Examples of processes to be monitored are quality assurance and configuration management. 3. Conduct reviews with the supplier as specified in the supplier agreement. Refer to the Project Monitoring and Control process area for more information about conducting reviews. Reviews cover both formal and informal reviews and include the following steps: · Preparing for the review · Ensuring that relevant stakeholders participate · Conducting the review · Identifying, documenting, and tracking all action items to closure · Preparing and distributing to the relevant stakeholders a summary report of the review 4. Conduct technical reviews with the supplier as defined in the supplier agreement. Technical reviews typically include the following: · Providing the supplier with visibility into the needs and desires of the project's customers and end users, as appropriate · Reviewing the supplier's technical activities and verifying that the supplier's interpretation and implementation of the requirements are consistent with the project's interpretation · Ensuring that technical commitments are being met and that technical issues are communicated and resolved in a timely manner · Obtaining technical information about the supplier's products · Providing appropriate technical information and support to the supplier 5. Conduct management reviews with the supplier as defined in the supplier agreement. Management reviews typically include the following: · Reviewing critical dependencies · Reviewing project risks involving the supplier · Reviewing schedule and budget Technical and management reviews may be coordinated and held jointly. 6. Use the results of reviews to improve the supplier's performance and to establish and nurture long-term relationships with preferred suppliers. 7. Monitor risks involving the supplier and take corrective action as necessary. Refer to the Project Monitoring and Control process area for more information about monitoring project risks. 8. Revise the supplier agreement and project plans and schedules as necessary.
SAM SP 2.3 | SP 2.3 Accept the Acquired Product Ensure that the supplier agreement is satisfied before accepting the acquired product. Acceptance reviews and tests and configuration audits should be completed before accepting the product as defined in the supplier agreement. Typical Work Products 1. Acceptance test procedures 2. Acceptance test results 3. Discrepancy reports or corrective action plans Subpractices 1. Define the acceptance procedures. 2. Review and obtain agreement with relevant stakeholders on the acceptance procedures before the acceptance review or test. 3. Verify that the acquired products satisfy their requirements. Refer to the Verification process area for more information about verifying products. 4. Confirm that the nontechnical commitments associated with the acquired work product are satisfied. This may include confirming that the appropriate license, warranty, ownership, usage, and support or maintenance agreements are in place and that all supporting materials are received. 5. Document the results of the acceptance review or test. 6. Establish and obtain supplier agreement on an action plan for any acquired work products that do not pass their acceptance review or test. 7. Identify, document, and track action items to closure. Refer to the Project Monitoring and Control process area for more information about tracking action items.
SAM SP 2.4 | SP 2.4 Transition Products Transition the acquired products from the supplier to the project. Before the acquired product is transferred to the project for integration, appropriate planning and evaluation should occur to ensure a smooth transition. Refer to the Product Integration process area for more information about integrating the acquired products. Typical Work Products 1. Transition plans 2. Training reports 3. Support and maintenance reports Subpractices 1. Ensure that there are appropriate facilities to receive, store, use, and maintain the acquired products. 2. Ensure that appropriate training is provided for those involved in receiving, storing, using, and maintaining the acquired products. 3. Ensure that storing, distributing, and using the acquired products are performed according to the terms and conditions specified in the supplier agreement or license.
Legenda Status - DEFINIÇÃO:
|  |  | TD | 0
|  |  | LD | 0
|  |  | PD | 0
|  |  | ND | 0
Note on D13: * Processo escrito e aderente
Note on D14: * Existem pendências não muito críticas
Note on D15: * Existe uma parte da prática nao atendida pela definição
Note on D16: * Não está definido em nenhum lugar do processo ou não está aderente

## MA
MA - Measurement and Analysis |  | Processo da Organização
Cód. | Práticas Específicas | Processo | Atividade | Artefato Direto | Artefato Indireto | Status Def.
M&A SP 1.1 | SP 1.1 Establish Measurement Objectives Establish and maintain measurement objectives that are derived from identified information needs and objectives. Measurement objectives document the purposes for which measurement and analysis are done, and specify the kinds of actions that may be taken based on the results of data analyses. The sources for measurement objectives may be management, technical, project, product, or process implementation needs. The measurement objectives may be constrained by existing processes, available resources, or other measurement considerations. Judgments may need to be made about whether the value of the results will be commensurate with the resources devoted to doing the work. Modifications to identified information needs and objectives may, in turn, be indicated as a consequence of the process and results of measurement and analysis. Sources of information needs and objectives may include the following: · Project plans · Monitoring of project performance · Interviews with managers and others who have information needs · Established management objectives · Strategic plans · Business plans · Formal requirements or contractual obligations · Recurring or other troublesome management or technical problems · Experiences of other projects or organizational entities · External industry benchmarks · Process-improvement plans Refer to the Project Planning process area for more information about estimating project attributes and other planning information needs. Refer to the Project Monitoring and Control process area for more information about project performance information needs. Refer to the Requirements Development process area for more information about meeting customer requirements and related information needs. Refer to the Requirements Management process area for more information about maintaining requirements traceability and related information needs. Typical Work Products 1. Measurement objectives 1. Document information needs and objectives. Information needs and objectives are documented to allow traceability to subsequent measurement and analysis activities. 2. Prioritize information needs and objectives. It may be neither possible nor desirable to subject all initially identified information needs to measurement and analysis. Priorities may also need to be set within the limits of available resources. 3. Document, review, and update measurement objectives. It is important to carefully consider the purposes and intended uses of measurement and analysis. The measurement objectives are documented, reviewed by management and other relevant stakeholders, and updated as necessary. Doing so enables traceability to subsequent measurement and analysis activities, and helps ensure that the analyses will properly address identified information needs and objectives. It is important that users of measurement and analysis results be involved in setting measurement objectives and deciding on plans of action. It may also be appropriate to involve those who provide the measurement data. 4. Provide feedback for refining and clarifying information needs and objectives as necessary. Identified information needs and objectives may need to be refined and clarified as a result of setting measurement objectives. Initial descriptions of information needs may be unclear or ambiguous. Conflicts may arise between existing needs and objectives. Precise targets on an already existing measure may be unrealistic. 5. Maintain traceability of the measurement objectives to the identified information needs and objectives. There must always be a good answer to the question, "Why are we measuring this?" Of course, the measurement objectives may also change to reflect evolving information needs and objectives. | Alinhar as Atividades de medição e análise | Estabelecer Objetivos de Medições | Plano de Métricas
M&A SP 1.2 | SP 1.2 Specify Measures Specify measures to address the measurement objectives. Measurement objectives are refined into precise, quantifiable measures. Measures may be either "base" or "derived." Data for base measures are obtained by direct measurement. Data for derived measures come from other data, typically by combining two or more base measures. Examples of commonly used base measures include the following: · Estimates and actual measures of work product size (e.g., number of pages) · Estimates and actual measures of effort and cost (e.g., number of person hours) · Quality measures (e.g., number of defects, number of defects by severity) Examples of commonly used derived measures include the following: · Earned Value · Schedule Performance Index · Defect density · Peer review coverage · Test or verification coverage · Reliability measures (e.g., mean time to failure) · Quality measures (e.g., number of defects by severity/total number of defects) Derived measures typically are expressed as ratios, composite indices, or other aggregate summary measures. They are often more quantitatively reliable and meaningfully interpretable than the base measures used to generate them. Typical Work Products 1. Specifications of base and derived measures Subpractices 1. Identify candidate measures based on documented measurement objectives. The measurement objectives are refined into specific measures. The identified candidate measures are categorized and specified by name and unit of measure. 2. Identify existing measures that already address the measurement objectives. Specifications for measures may already exist, perhaps established for other purposes earlier or elsewhere in the organization. 3. Specify operational definitions for the measures. Operational definitions are stated in precise and unambiguous terms. They address two important criteria as follows: · Communication: What has been measured, how was it measured, what are the units of measure, and what has been included or excluded? · Repeatability: Can the measurement be repeated, given the same definition, to get the same results? 4. Prioritize, review, and update measures. Proposed specifications of the measures are reviewed for their appropriateness with potential end users and other relevant stakeholders. Priorities are set or changed, and specifications of the measures are updated as necessary. | Alinhar as Atividades de medição e análise | Especificar Medidas | Especificações Métricas | Plano de Métricas
M&A SP 1.3 | SP 1.3 Specify Data Collection and Storage Procedures Specify how measurement data will be obtained and stored. Explicit specification of collection methods helps ensure that the right data are collected properly. It may also aid in further clarifying information needs and measurement objectives. Proper attention to storage and retrieval procedures helps ensure that data are available and accessible for future use. Typical Work Products 1. Data collection and storage procedures 2. Data collection tools Subpractices 1. Identify existing sources of data that are generated from current work products, processes, or transactions. Existing sources of data may already have been identified when specifying the measures. Appropriate collection mechanisms may exist whether or not pertinent data have already been collected. 2. Identify measures for which data are needed, but are not currently available. 3. Specify how to collect and store the data for each required measure. Explicit specifications are made of how, where, and when the data will be collected. Procedures for collecting valid data are specified. The data are stored in an accessible manner for analysis, and it is determined whether they will be saved for possible reanalysis or documentation purposes. Questions to be considered typically include the following: · Have the frequency of collection and the points in the process where measurements will be made been determined? · Has the time line that is required to move measurement results from the points of collection to repositories, other databases, or end users been established? · Who is responsible for obtaining the data? · Who is responsible for data storage, retrieval, and security? · Have necessary supporting tools been developed or acquired? 4. Create data collection mechanisms and process guidance. Data collection and storage mechanisms are well integrated with other normal work processes. Data collection mechanisms may include manual or automated forms and templates. Clear, concise guidance on correct procedures is available to those responsible for doing the work. Training is provided as necessary to clarify the processes necessary for collection of complete and accurate data and to minimize the burden on those who must provide and record the data. 5. Support automatic collection of the data where appropriate and feasible. Automated support can aid in collecting more complete and accurate data. Examples of such automated support include the following: · Timestamped activity logs · Static or dynamic analyses of artifacts However, some data cannot be collected without human intervention (e.g., customer satisfaction or other human judgments), and setting up the necessary infrastructure for other automation may be costly. 6. Prioritize, review, and update data collection and storage procedures. Proposed procedures are reviewed for their appropriateness and feasibility with those who are responsible for providing, collecting, and storing the data. They also may have useful insights about how to improve existing processes, or be able to suggest other useful measures or analyses. 7. Update measures and measurement objectives as necessary. Priorities may need to be reset based on the following: · The importance of the measures · The amount of effort required to obtain the data Considerations include whether new forms, tools, or training would be required to obtain the data. | Alinhar as Atividades de medição e análise | Especificar Procedimentos de Coleta e armazenamento de Dados | Procedimentos de coleta e armazenamento de dados
M&A SP 1.4 | SP 1.4 Specify Analysis Procedures Specify how measurement data will be analyzed and reported. Specifying the analysis procedures in advance ensures that appropriate analyses will be conducted and reported to address the documented measurement objectives (and thereby the information needs and objectives on which they are based). This approach also provides a check that the necessary data will in fact be collected. Typical Work Products 1. Analysis specification and procedures 2. Data analysis tools Subpractices 1. Specify and prioritize the analyses that will be conducted and the reports that will be prepared. Early attention should be paid to the analyses that will be conducted and to the manner in which the results will be reported. These should meet the following criteria: · The analyses explicitly address the documented measurement objectives · Presentation of the results is clearly understandable by the audiences to whom the results are addressed Priorities may have to be set within available resources. 2. Select appropriate data analysis methods and tools. Refer to the Select Measures and Analytic Techniques and Apply Statistical Methods to Understand Variation specific practices of the Quantitative Project Management process area for more information about the appropriate use of statistical analysis techniques and understanding variation, respectively. Issues to be considered typically include the following: · Choice of visual display and other presentation techniques (e.g., pie charts, bar charts, histograms, radar charts, line graphs, scatter plots, or tables) · Choice of appropriate descriptive statistics (e.g., arithmetic mean, median, or mode) · Decisions about statistical sampling criteria when it is impossible or unnecessary to examine every data element · Decisions about how to handle analysis in the presence of missing data elements · Selection of appropriate analysis tools Descriptive statistics are typically used in data analysis to do the following: · Examine distributions on the specified measures (e.g., central tendency, extent of variation, data points exhibiting unusual variation) · Examine the interrelationships among the specified measures (e.g., comparisons of defects by phase of the product's life cycle or by product component) · Display changes over time 3. Specify administrative procedures for analyzing the data and communicating the results. Issues to be considered typically include the following: · Identifying the persons and groups responsible for analyzing the data and presenting the results · Determining the time line to analyze the data and present the results · Determining the venues for communicating the results (e.g., progress reports, transmittal memos, written reports, or staff meetings) 4. Review and update the proposed content and format of the specified analyses and reports. All of the proposed content and format are subject to review and revision, including analytic methods and tools, administrative procedures, and priorities. The relevant stakeholders consulted should include intended end users, sponsors, data analysts, and data providers. 5. Update measures and measurement objectives as necessary. Just as measurement needs drive data analysis, clarification of analysis criteria can affect measurement. Specifications for some measures may be refined further based on the specifications established for data analysis procedures. Other measures may prove to be unnecessary, or a need for additional measures may be recognized. The exercise of specifying how measures will be analyzed and reported may also suggest the need for refining the measurement objectives themselves. 6. Specify criteria for evaluating the utility of the analysis results, and of the conduct of the measurement and analysis activities. Criteria for evaluating the utility of the analysis might address the extent to which the following apply: · The results are (1) provided on a timely basis, (2) understandable, and (3) used for decision making. · The work does not cost more to perform than is justified by the benefits that it provides. Criteria for evaluating the conduct of the measurement and analysis might include the extent to which the following apply: · The amount of missing data or the number of flagged inconsistencies is beyond specified thresholds. · There is selection bias in sampling (e.g., only satisfied end users are surveyed to evaluate end-user satisfaction, or only unsuccessful projects are evaluated to determine overall productivity). · The measurement data are repeatable (e.g., statistically reliable). · Statistical assumptions have been satisfied (e.g., about the distribution of data or about appropriate measurement scales). | Alinhar as Atividades de medição e análise | Especificar Procedimento de Análises | Procedimentos de análise
M&A SP 2.1 | SP 2.1 Collect Measurement Data Obtain specified measurement data. The data necessary for analysis are obtained and checked for completeness and integrity. Typical Work Products 1. Base and derived measurement data sets 2. Results of data integrity tests Subpractices 1. Obtain the data for base measures. Data are collected as necessary for previously used as well as for newly specified base measures. Existing data are gathered from project records or from elsewhere in the organization. Note that data that were collected earlier may no longer be available for reuse in existing databases, paper records, or formal repositories. 2. Generate the data for derived measures. Values are newly calculated for all derived measures. 3. Perform data integrity checks as close to the source of the data as possible. All measurements are subject to error in specifying or recording data. It is always better to identify such errors and to identify sources of missing data early in the measurement and analysis cycle. Checks can include scans for missing data, out-of-bounds data values, and unusual patterns and correlation across measures. It is particularly important to do the following: · Test and correct for inconsistency of classifications made by human judgment (i.e., to determine how frequently people make differing classification decisions based on the same information, otherwise known as "inter-coder reliability"). · Empirically examine the relationships among the measures that are used to calculate additional derived measures. Doing so can ensure that important distinctions are not overlooked and that the derived measures convey their intended meanings (otherwise known as "criterion validity"). | Fornecer Resultados de Medições | Coletar Dados de Medições | Conjuntos de dados de medições básicas e derivadas; Relatório de testes de integridade dos dados; | Relatório com análises
M&A SP 2.2 | SP 2.2 Analyze Measurement Data Analyze and interpret measurement data. The measurement data are analyzed as planned, additional analyses are conducted as necessary, results are reviewed with relevant stakeholders, and necessary revisions for future analyses are noted. Typical Work Products 1. Analysis results and draft reports Subpractices 1. Conduct initial analyses, interpret the results, and draw preliminary conclusions. The results of data analyses are rarely self evident. Criteria for interpreting the results and drawing conclusions should be stated explicitly. 2. Conduct additional measurement and analysis as necessary, and prepare results for presentation. The results of planned analyses may suggest (or require) additional, unanticipated analyses. In addition, they may identify needs to refine existing measures, to calculate additional derived measures, or even to collect data for additional primitive measures to properly complete the planned analysis. Similarly, preparing the initial results for presentation may identify the need for additional, unanticipated analyses. 3. Review the initial results with relevant stakeholders. It may be appropriate to review initial interpretations of the results and the way in which they are presented before disseminating and communicating them more widely. Reviewing the initial results before their release may prevent needless misunderstandings and lead to improvements in the data analysis and presentation. Relevant stakeholders with whom reviews may be conducted include intended end users and sponsors, as well as data analysts and data providers. 4. Refine criteria for future analyses. Valuable lessons that can improve future efforts are often learned from conducting data analyses and preparing results. Similarly, ways to improve measurement specifications and data collection procedures may become apparent, as may ideas for refining identified information needs and objectives. | Fornecer Resultados de Medições | Analisar Dados de Medições | Relatórios preliminares. | Conjuntos de dados de medições básicas e derivadas
M&A SP 2.3 | SP 2.3 Store Data and Results Manage and store measurement data, measurement specifications, and analysis results. Storing measurement-related information enables the timely and cost-effective future use of historical data and results. The information also is needed to provide sufficient context for interpretation of the data, measurement criteria, and analysis results. Information stored typically includes the following: · Measurement plans · Specifications of measures · Sets of data that have been collected · Analysis reports and presentations The stored information contains or references the information needed to understand and interpret the measures and assess them for reasonableness and applicability (e.g., measurement specifications used on different projects when comparing across projects). Data sets for derived measures typically can be recalculated and need not be stored. However, it may be appropriate to store summaries based on derived measures (e.g., charts, tables of results, or report prose). Interim analysis results need not be stored separately if they can be efficiently reconstructed. Projects may choose to store project-specific data and results in a project-specific repository. When data are shared more widely across projects, the data may reside in the organization's measurement repository. Refer to the Establish the Organization's Measurement Repository specific practice of the Organizational Process Definition process area for more information about establishing the organization's measurement repository. Refer to the Configuration Management process area for information on managing measurement work products. Typical Work Products 1. Stored data inventory Subpractices 1. Review the data to ensure their completeness, integrity, accuracy, and currency. 2. Make the stored contents available for use only by appropriate groups and personnel. 3. Prevent the stored information from being used inappropriately. Examples of ways to prevent inappropriate use of the data and related information include controlling access to data and educating people on the appropriate use of data. Examples of inappropriate use include the following: · Disclosure of information that was provided in confidence · Faulty interpretations based on incomplete, out-of-context, or otherwise misleading information · Measures used to improperly evaluate the performance of people or to rank projects · Impugning the integrity of specific individuals | Fornecer Resultados de Medições | Armazenar Dados e Resultados | Catálogo dos dados armazenados
M&A SP 2.4 | SP 2.4 Communicate Results Report results of measurement and analysis activities to all relevant stakeholders. The results of the measurement and analysis process are communicated to relevant stakeholders in a timely and usable fashion to support decision making and assist in taking corrective action. Relevant stakeholders include intended users, sponsors, data analysts, and data providers. Typical Work Products 1. Delivered reports and related analysis results 2. Contextual information or guidance to aid in the interpretation of analysis results Subpractices 1. Keep relevant stakeholders apprised of measurement results on a timely basis. Measurement results are communicated in time to be used for their intended purposes. Reports are unlikely to be used if they are distributed with little effort to follow up with those who need to know the results. To the extent possible and as part of the normal way they do business, users of measurement results are kept personally involved in setting objectives and deciding on plans of action for measurement and analysis. The users are regularly kept apprised of progress and interim results. Refer to the Project Monitoring and Control process area for more information on the use of measurement results. 2. Assist relevant stakeholders in understanding the results. Results are reported in a clear and concise manner appropriate to the methodological sophistication of the relevant stakeholders. They are understandable, easily interpretable, and clearly tied to identified information needs and objectives. The data are often not self evident to practitioners who are not measurement experts. Measurement choices should be explicitly clear about the following: · How and why the base and derived measures were specified · How the data were obtained · How to interpret the results based on the data analysis methods that were used · How the results address their information needs Examples of actions to assist in understanding of results include the following: · Discussing the results with the relevant stakeholders · Providing a transmittal memo that provides background and explanation · Briefing users on the results · Providing training on the appropriate use and understanding of measurement results | Fornecer Resultados de Medições | Comunicar Resultados | Relatório com análises | Auxílio para análise
Legenda Status - DEFINIÇÃO:
|  |  | TD | 0
|  |  | LD | 0
|  |  | PD | 0
|  |  | ND | 0
Note on D14: * Processo escrito e aderente
Note on D15: * Existem pendências não muito críticas
Note on D16: * Existe uma parte da prática nao atendida pela definição
Note on D17: * Não está definido em nenhum lugar do processo ou não está aderente

## PPQA
PPQA - Process and Product Quality Assurance |  | Processo da Organização
Cód. | Práticas Específicas | Processo | Atividade | Artefato Direto | Artefato Indireto | Status Def.
PPQA SP 1.1 | SP 1.1 Objectively Evaluate Processes Objectively evaluate the designated performed processes against the applicable process descriptions, standards, and procedures. Objectivity in quality assurance evaluations is critical to the success of the project. A description of the quality assurance reporting chain and how it ensures objectivity should be defined. Typical Work Products 1. Evaluation reports 2. Noncompliance reports 3. Corrective actions Subpractices 1. Promote an environment (created as part of project management) that encourages employee participation in identifying and reporting quality issues. 2. Establish and maintain clearly stated criteria for the evaluations. The intent of this subpractice is to provide criteria, based on business needs, such as the following: · What will be evaluated · When or how often a process will be evaluated · How the evaluation will be conducted · Who must be involved in the evaluation 3. Use the stated criteria to evaluate performed processes for adherence to process descriptions, standards, and procedures. 4. Identify each noncompliance found during the evaluation. 5. Identify lessons learned that could improve processes for future products and services. | Avaliar Objetivamente processos e Produtos de Trabalho | Avaliar Objetivamente os Processos | Relatório de Ações Corretivas do Processo; Relatório de Critérios de Avaliação do Processo; Relatório de Não-Conformidades do Processo ; | Relatório de Critérios de Avaliação do Processo; Relatório de Não-Conformidades do Processo;
PPQA SP 1.2 | SP 1.2 Objectively Evaluate Work Products and Services Objectively evaluate the designated work products and services against the applicable process descriptions, standards, and procedures. Typical Work Products 1. Evaluation reports 2. Noncompliance reports 3. Corrective actions Subpractices 1. Select work products to be evaluated, based on documented sampling criteria if sampling is used. 2. Establish and maintain clearly stated criteria for the evaluation of work products. The intent of this subpractice is to provide criteria, based on business needs, such as the following: · What will be evaluated during the evaluation of a work product · When or how often a work product will be evaluated · How the evaluation will be conducted · Who must be involved in the evaluation 3. Use the stated criteria during the evaluations of work products. 4. Evaluate work products before they are delivered to the customer. 5. Evaluate work products at selected milestones in their development. 6. Perform in-progress or incremental evaluations of work products and services against process descriptions, standards, and procedures. 7. Identify each case of noncompliance found during the evaluations. 8. Identify lessons learned that could improve processes for future products and services. | Avaliar Objetivamente processos e Produtos de Trabalho | Avaliar Objetivamente Produtos de Trabalho e Serviços | Relatório de Ações Corretivas dos Produtos ou Serviços ; Relatório de Critérios de Avaliação do Produto e Serviço; Relatório de Não-Conformidades do Produtoe Serviço; | Relatório de Critérios de Avaliação do Produto e Serviço; Relatório de Não-Conformidades do Produto e Serviço.
PPQA SP 2.1 | SP 2.1 Communicate and EnsureResolution of Noncompliance Issues Communicate quality issues and ensure resolution of noncompliance issues with the staff and managers. Noncompliance issues are problems identified in evaluations that reflect a lack of adherence to applicable standards, process descriptions, or procedures. The status of noncompliance issues provides an indication of quality trends. Quality issues include noncompliance issues and results of trend analysis. When local resolution of noncompliance issues cannot be obtained, use established escalation mechanisms to ensure that the appropriate level of management can resolve the issue. Track noncompliance issues to resolution. Typical Work Products 1. Corrective action reports 2. Evaluation reports 3. Quality trends Subpractices 1. Resolve each noncompliance with the appropriate members of the staff where possible. 2. Document noncompliance issues when they cannot be resolved within the project. Examples of ways to resolve noncompliance within the project include the following: · Fixing the noncompliance · Changing the process descriptions, standards, or procedures that were violated · Obtaining a waiver to cover the noncompliance issue 3. Escalate noncompliance issues that cannot be resolved within the project to the appropriate level of management designated to receive and act on noncompliance issues. 4. Analyze the noncompliance issues to see if there are any quality trends that can be identified and addressed. 5. Ensure that relevant stakeholders are aware of the results of evaluations and the quality trends in a timely manner. 6. Periodically review open noncompliance issues and trends with the manager designated to receive and act on noncompliance issues. 7. Track noncompliance issues to resolution. | Fornecer um Entendimento Objetivo | Comunicar e Garantir a Solução de Não-conformidades | Relatório de Ações Corretivas do Processo; Relatório de Ações Corretivas dos Produtos e Serviços; Relatórios de avaliações; Tendências de qualidade;
PPQA SP 2.2 | SP 2.2 Establish Records Establish and maintain records of the quality assurance activities. Typical Work Products 1. Evaluation logs 2. Quality assurance reports 3. Status reports of corrective actions 4. Reports of quality trends Subpractices 1. Record process and product quality assurance activities in sufficient detail such that status and results are known. 2. Revise the status and history of the quality assurance activities as necessary. | Fornecer um Entendimento Objetivo | Estabelecer Registros | Relatórios de avaliações; Relatórios de estado de ações corretivas; Relatórios de garantia da qualidade; Relatórios sobre tendências em relação à qualidade;
Legenda Status - DEFINIÇÃO:
|  |  | TD | 0
|  |  | LD | 0
|  |  | PD | 0
|  |  | ND | 0
Note on D10: * Processo escrito e aderente
Note on D11: * Existem pendências não muito críticas
Note on D12: * Existe uma parte da prática nao atendida pela definição
Note on D13: * Não está definido em nenhum lugar do processo ou não está aderente

## CM
CM - Configuration Management |  | Processo da Organização
Cód. | Práticas Específicas | Processo | Atividade | Artefato Direto | Artefato Indireto | Status Def.
CM SP 1.1 | SP 1.1 Identify Configuration Items Identify the configuration items, components, and related work products that will be placed under configuration management. Configuration identification is the selection, creation, and specification of the following: · Products that are delivered to the customer · Designated internal work products · Acquired products · Tools · Other items that are used in creating and describing these work products Items under configuration management will include specifications and interface documents that define the requirements for the product. Other documents, such as test results, may also be included, depending on their criticality to defining the product. A "configuration item" is an entity designated for configuration management, which may consist of multiple related work products that form a baseline. This logical grouping provides ease of identification and controlled access. The selection of work products for configuration management should be based on criteria established during planning. For Systems Engineering In a system that includes both hardware and software, where software represents a small part of the system, all of the software may be designated as a single configuration item. In other cases, the software may be decomposed into multiple configuration items. Configuration items can be decomposed into configuration components and configuration units. Only the term "configuration item" is used in this process area. In these practices, "configuration item" may be interpreted as "configuration component" or "configuration unit" as appropriate. For example, configuration items in the area of requirements management could vary from each individual requirement to a set of requirements. Typical Work Products 1. Identified configuration items Subpractices 1. Select the configuration items and the work products that compose them based on documented criteria. Example criteria for selecting configuration items at the appropriate work product level include the following: · Work products that may be used by two or more groups · Work products that are expected to change over time either because of errors or change of requirements · Work products that are dependent on each other in that a change in one mandates a change in the others · Work products that are critical for the project Examples of work products that may be part of a configuration item include the following: · Process descriptions · Requirements · Design . Test plans and procedures · Test results · Interface descriptions For Software Engineering Examples of software work products that may be part of a configuration item include the following: · Code/module · Tools (e.g., compilers) 2. Assign unique identifiers to configuration items. 3. Specify the important characteristics of each configuration item. Example characteristics of configuration items include author, document or file type, and programming language for software code files. 4. Specify when each configuration item is placed under configuration management. Example criteria for determining when to place work products under configuration management include the following: · Stage of the project life cycle · When the work product is ready for test · Degree of control desired on the work product · Cost and schedule limitations · Customer requirements 5. Identify the owner responsible for each configuration item.
CM SP 1.2 | SP 1.2 Establish a Configuration Management System Establish and maintain a configuration management and change management system for controlling work products. A configuration management system includes the storage media, the procedures, and the tools for accessing the configuration system. A change management system includes the storage media, the procedures, and tools for recording and accessing change requests. Typical Work Products 1. Configuration management system with controlled work products 2. Configuration management system access control procedures 3. Change request database Subpractices 1. Establish a mechanism to manage multiple control levels of configuration management. Examples of situations leading to multiple levels of control include the following: · Differences in the levels of control needed at different times in the project life cycle (e.g., tighter control as product matures) · Differences in the levels of control needed for different types of systems (e.g., software-only systems versus systems that include hardware and software) · Differences in the levels of control needed to satisfy privacy and security requirements for the configuration items 2. Store and retrieve configuration items in the configuration management system. Examples of configuration management systems include the following: · Dynamic (or developer's) systems contain components currently being created or revised. They are in the developer's workspace and are controlled by the developer. Configuration items in a dynamic system are under version control. · Master (or controlled) systems contain current baselines and changes to them. Configuration items in a master system are under full configuration management as described in this process area. · Static systems contain archives of various baselines released for use. Static systems are under full configuration management as described in this process area. 3. Share and transfer configuration items between control levels within the configuration management system. 4. Store and recover archived versions of configuration items. 5. Store, update, and retrieve configuration management records. 6. Create configuration management reports from the configuration management system. 7. Preserve the contents of the configuration management system. Examples of preservation functions of the configuration management system include the following: · Backups and restoration of configuration management files · Archiving of configuration management files · Recovery from configuration management errors 8. Revise the configuration management structure as necessary.
CM SP 1.3 | SP 1.3 Create or Release Baselines Create or release baselines for internal use and for delivery to the customer. A baseline is a set of specifications or work products that has been formally reviewed and agreed upon, that thereafter serves as the basis for further development, and that can be changed only through change control procedures. A baseline represents the assignment of an identifier to a configuration item and its associated entities. For Systems Engineering Release of a baseline involves approving a set of configuration data for the agreed-upon set of configuration items from the configuration management system and releasing the baseline for further development. Multiple baselines may be used to define an evolving product during its development cycle. One common set includes the system-level requirements, system-element-level design requirements, and the product definition at the end of development/beginning of production. These are referred to as the "functional baseline," "allocated baseline," and "product baseline." For Software Engineering A set of requirements, design, source code files and the associated executable code, build files, and user documentation (associated entities) that have been assigned a unique identifier can be considered to be a baseline. Release of a baseline constitutes retrieval of source code files (configuration items) from the configuration management system and generating the executable files. A baseline that is delivered to a customer is typically called a "release" whereas a baseline for an internal use is typically called a "build." Typical Work Products 1. Baselines 2. Description of baselines Subpractices 1. Obtain authorization from the configuration control board (CCB) before creating or releasing baselines of configuration items. 2. Create or release baselines only from configuration items in the configuration management system. For Systems Engineering Ensure that the configuration items are built to the correct drawing. 3. Document the set of configuration items that are contained in a baseline. 4. Make the current set of baselines readily available.
CM SP 2.1 | SP 2.1 Track Change Requests Track change requests for the configuration items Change requests address not only new or changed requirements, but also failures and defects in the work products. Change requests are analyzed to determine the impact that the change will have on the work product, related work products, and schedule and cost. Typical Work Products 1. Change Requests Subpractices 1. Initiate and record change requests in the change request database. 2. Analyze the impact of changes and fixes proposed in the change. Changes are evaluated through activities that ensure that they are consistent with all technical and project requirements. Changes are evaluated for their impact beyond inmediate project or contact requirements. Changes to an item used in multiple products can resolve an inmediate issue while causing a problem in other applications. 3. Review change requests that will be addressed in the next baseline with those who will be affected by the changes and get their agreement. Conduct the change request review with appropriate participants. Record the disposition of each change request and the rationale for the decision, including success criteria, a brief action plan as appropriate, and needs met or unmet by the change. Perform the actions required in the disposition, and report the results to relevant stakeholders. 4. Track the status of change requests to closure. Change requests brought into the system need to be handled in a proficient and timely manner. Once a change request has been processed, it is critical to close the request with the appropriate approved action as soon as it is practical. Actions left open result in larger than necessary status lists, which in turn result in added costs and confusion.
CM SP 2.2 | SP 2.2 Control Configuration Items Control changes to the configuration items. Control is maintained over the configuration of the work product baseline. This control includes tracking the configuration of each of the configuration items, approving a new configuration if necessary, and updating the baseline. Typical Work Products 1. Revision history of configuration items 2. Archives of the baselines Subpractices 1. Control changes to configuration items throughout the life of the product. 2. Obtain appropriate authorization before changed configuration items are entered into the configuration management system. For example, authorization may come from the CCB, the project manager, or the customer. 3. Check in and check out configuration items from the configuration management system for incorporation of changes in a manner that maintains the correctness and integrity of the configuration items. Examples of check-in and check-out steps include the following: · Confirming that the revisions are authorized · Updating the configuration items · Archiving the replaced baseline and retrieving the new baseline 4. Perform reviews to ensure that changes have not caused unintended effects on the baselines (e.g., ensure that the changes have not compromised the safety and/or security of the system). 5. Record changes to configuration items and the reasons for the changes as appropriate. If a proposed change to the work product is accepted, a schedule is identified for incorporating the change into the work product and other affected areas. Configuration control mechanisms can be tailored to categories of changes. For example, the approval considerations could be less stringent for component changes that do not affect other components. Changed configuration items are released after review and approval of configuration changes. Changes are not official until they are released.
CM SP 3.1 | SP 3.1 Establish Configuration Management Records Establish and maintain records describing configuration items. Typical Work Products 1. Revision history of configuration items 2. Change log 3. Copy of the change requests 4. Status of configuration items 5. Differences between baselines Subpractices 1. Record configuration management actions in sufficient detail so the content and status of each configuration item is known and previous versions can be recovered. 2. Ensure that relevant stakeholders have access to and knowledge of the configuration status of the configuration items. Examples of activities for communicating configuration status include the following: · Providing access permissions to authorized end users · Making baseline copies readily available to authorized end users 3. Specify the latest version of the baselines. 4. Identify the version of configuration items that constitute a particular baseline. 5. Describe the differences between successive baselines. 6. Revise the status and history (i.e., changes and other actions) of each configuration item as necessary.
CM SP 3.2 | SP 3.2 Perform Configuration Audits Perform configuration audits to maintain integrity of the configuration baselines. Audit configuration management activities and processes to confirm that the resulting baselines and documentation are accurate, and record the audit results as appropriate. Typical Work Products 1. Configuration audit results 2. Action items Subpractices 1. Assess the integrity of the baselines. 2. Confirm that the configuration records correctly identify the configuration of the configuration items. 3. Review the structure and integrity of the items in the configuration management system. 4. Confirm the completeness and correctness of the items in the configuration management system. Completeness and correctness of the content is based on the requirements as stated in the plan and the disposition of approved change requests. 5. Confirm compliance with applicable configuration management standards and procedures. 6. Track action items from the audit to closure.
Legenda Status - DEFINIÇÃO:
|  |  | TD | 0
|  |  | LD | 0
|  |  | PD | 0
|  |  | ND | 0
Note on D13: * Processo escrito e aderente
Note on D14: * Existem pendências não muito críticas
Note on D15: * Existe uma parte da prática nao atendida pela definição
Note on D16: * Não está definido em nenhum lugar do processo ou não está aderente